## Configuration
PROJECT CONFIGURATION
Project Settings
Embedment Tolerance (ft): | 1 | Change this value to adjust your project tolerance
Pile Types (Customize Your Types Here)
Pile Type Name | Description (Optional)
Type A | 12" Square Concrete Piles
Type B | 14" Square Concrete Piles
Type C | 16" Square Concrete Piles
Type D | H-Piles
Add more types as needed...
INSTRUCTIONS: Edit the Pile Type names above to match your project. The dropdowns in Plot Plan and Field Data Entry will automatically use these values. Add or remove rows as needed.

## Plot Plan
Pile Name | Pile Type | Block | Design Embedment (ft) | Location/Grid | Custom Field 1 | Custom Field 2 | Custom Field 3 | Notes
P-001 | Type A | Block 1 | 45 | Grid A1
P-002 | Type A | Block 1 | 45 | Grid A2
P-003 | Type B | Block 1 | 50 | Grid A3
P-004 | Type B | Block 2 | 50 | Grid B1
P-005 | Type C | Block 2 | 55 | Grid B2

## Field Data Entry
Date | Pile Name | Inspector | Start Time | End Time | Drive Time (min) | Embedment (ft) | Refusal | Status | Design Embedment (ft) | Pile Type | Block | Custom Field 1 | Custom Field 2 | Custom Field 3 | Notes
2025-01-15 | P-001 | John Smith | 08:00 | 08:45 |  | 46 | No
2025-01-15 | P-002 | John Smith | 09:00 | 09:30 |  | 44.5 | No
2025-01-16 | P-003 | Jane Doe | 10:00 | 11:15 |  | 51 | No
2025-01-16 | P-004 | Jane Doe | 13:00 | 13:25 |  | 48 | No
2025-01-17 | P-005 | John Smith | 08:30 | 09:45 |  | 53 | Yes

## Dashboard
PILE TRACKER PRO - DASHBOARD
PROJECT INFORMATION
Embedment Tolerance (ft):
Report Generated:
OVERALL STATISTICS |  |  | BY PILE TYPE
Metric | Count | Percentage | Type | Planned | Installed
Total Piles Planned |  | -
Total Piles Installed |  | -
Accepted
Tolerance
Refusal
Pending
Refusals (Yes)
Slow Drive (>60 min)
INSTRUCTIONS
1. PLOT PLAN: Enter your expected pile data (paste from your plot plan). This is your master list of piles to be installed.
2. FIELD DATA ENTRY: Enter actual installation data. The spreadsheet will auto-populate pile type, block, and design embedment.
3. FORMULAS: Drive time, status, and lookups are calculated automatically. Don't edit formula columns.
4. STATUS CODES: Accepted (green), Tolerance (yellow), Refusal (red), Pending (gray)
5. DASHBOARD: View real-time statistics and progress. All charts update automatically.
6. TOLERANCE: Default is 1 ft. Modify in cell C5 if your project uses a different tolerance.

## Block Analysis
Block | Total Piles | Accepted | Tolerance | Refusal | Pending | % Complete | Avg Drive Time
Block 1
Block 2
Block 3
Block 4

## Instructions
PILETRACKER PRO - USER GUIDE & INSTRUCTIONS
Welcome to PileTrackerPro!
This Excel template replicates the functionality of the PileTrackerPro web application, allowing you to track pile installation data offline with automatic calculations, visual analytics, and professional reporting.
CUSTOMIZATION & FLEXIBILITY
Configuration Sheet - Your Control Center
The Configuration sheet is where you customize the template to match your project. Here you can: (1) Change the embedment tolerance, (2) Edit pile type names to match your engineering specs, (3) Add or remove pile types as needed. All dropdowns and formulas automatically update when you change these settings!
Flexible CSV Import
Different engineering companies provide different CSV formats. This template includes 3 Custom Fields in both Plot Plan and Field Data Entry sheets. You can rename these column headers to match your CSV columns (e.g., "Pile Length", "Diameter", "Contractor", etc.) and paste your data directly. The core formulas won't be affected.
How to Change Pile Types
Go to Configuration sheet → Edit the Pile Type Name column (cells B9-B20). Your changes will automatically update: (1) Dropdown lists in Plot Plan, (2) Dashboard "By Pile Type" section, (3) All references throughout the workbook. You can have as many or as few pile types as your project requires.
HOW TO USE THIS SPREADSHEET
1. Configure Your Project in CONFIGURATION Sheet
Start here! Customize pile types to match your engineering specifications. Edit the pile type names in column B (cells B9-B20) - these will auto-populate in all dropdowns. Adjust the embedment tolerance if your project uses a different value than the default 1 ft. This sheet is your control center for project-specific settings.
2. Enter Plot Plan Data in PLOT PLAN Sheet
This is your master list of expected piles. Paste your pile plot plan data here, or enter it manually. The template includes 3 Custom Fields - rename these headers to match any extra columns in your CSV (e.g., "Pile Length", "Diameter"). Pile Type dropdown will show your configured types from step 1.
3. Enter Field Data in FIELD DATA ENTRY Sheet
As piles are installed, log the actual data here. When you enter a Pile Name that exists in the Plot Plan, the Design Embedment, Pile Type, and Block will auto-populate via VLOOKUP formulas. Enter the date, inspector name, start/end times, embedment, and whether there was refusal. The Drive Time and Status will calculate automatically using your configured tolerance.
4. Monitor Progress on the DASHBOARD
View real-time statistics including total piles planned vs installed, status breakdown (Accepted/Tolerance/Refusal/Pending), and performance metrics. All numbers update automatically as you add field data. The "By Pile Type" section dynamically shows your configured pile types.
5. Analyze Performance in BLOCK ANALYSIS
See detailed metrics for each block including acceptance rates, average drive times, and completion percentages. Great for identifying problem areas or high-performing blocks.
UNDERSTANDING STATUS CODES
ACCEPTED: Embedment is greater than or equal to Design Embedment. Pile meets specifications.
TOLERANCE: Embedment is within tolerance range (Design Embedment - Tolerance to Design Embedment). May require engineering review.
REFUSAL: Embedment is below Design Embedment minus Tolerance. Requires immediate attention and likely remediation.
PENDING: No embedment data entered yet. Pile installation not completed or data not recorded.
PRO TIPS & BEST PRACTICES
✓ CUSTOMIZE PILE TYPES in the Configuration sheet (cells B9-B20). All dropdowns, formulas, and the Dashboard will automatically update. This is the easiest way to match your project specifications.
✓ The embedment tolerance is set to 1 ft by default in Configuration sheet (cell C5). Change this value if your project uses a different tolerance. All status calculations will update automatically.
✓ CUSTOM FIELDS: Rename the "Custom Field 1/2/3" column headers in Plot Plan and Field Data Entry to match your CSV files. This makes importing data from different engineering companies much easier.
✓ Don't delete or modify the formula columns in Field Data Entry (Drive Time, Status, Design Embedment, Pile Type, Block). These auto-calculate based on your input.
✓ To add more pile types: Go to Configuration sheet → Add new type names in column B below row 13 → They'll automatically appear in all dropdowns.
✓ When adding new rows in Field Data Entry, copy the formulas down from the row above to ensure calculations continue working.
✓ The Plot Plan is your source of truth. Make sure pile names match exactly between Plot Plan and Field Data Entry for the VLOOKUP formulas to work.
✓ Use the Dashboard as a printable progress report. Hide gridlines are already off for a clean presentation.
✓ Slow drives are highlighted automatically when drive time exceeds 60 minutes. This threshold is hardcoded but can be modified in the conditional formatting rules.
✓ The spreadsheet works in Excel, Google Sheets, and LibreOffice Calc. Some advanced formatting may vary slightly between applications.
✓ Sample data is included in each sheet. You can delete it and start fresh, or modify it to match your project.
✓ Time entries (Start Time, End Time) can be entered in various formats: "8:00 AM", "08:00", "0800", etc. The drive time formula will handle most formats.
✓ Data validation prevents common errors (Pile Type dropdown, Refusal Yes/No). You can add more validation rules in Data → Data Validation.
✓ To add charts or pivot tables, use Excel's built-in tools with the Field Data Entry or Block Analysis sheets as source data.
✓ Back up your file regularly, especially before making major changes like deleting rows or modifying formulas.
✓ The Refusal column (Yes/No) is different from Refusal status. "Refusal: Yes" means the pile hit refusal during driving. Status "Refusal" means embedment is below tolerance.
✓ If you reorganize columns, update the VLOOKUP formulas accordingly. The current formulas reference specific column numbers.
KEY FORMULAS EXPLAINED
Drive Time Calculation:
=((TIMEVALUE(End Time)-TIMEVALUE(Start Time))*24*60)
Converts time difference to minutes. Multiplies by 24 (hours) then 60 (minutes).
Status Calculation:
=IF(Embedment="","Pending",IF(Embedment>=Design,"Accepted",IF(Embedment>=(Design-Tolerance),"Tolerance","Refusal")))
Nested IF statement that compares actual embedment against design embedment and tolerance to determine status.
Design Embedment Lookup:
=IFERROR(VLOOKUP(PileName,PlotPlan!A:D,4,FALSE),"")
Looks up the pile name in Plot Plan and returns the design embedment (column 4). IFERROR handles missing piles gracefully.
Percentage Complete:
=IF(Total>0,(Total-Pending)/Total,0)
Calculates completion rate by subtracting pending piles from total, then dividing by total.
TROUBLESHOOTING
Problem: VLOOKUP returns blank or #N/A error
Solution: Make sure the pile name in Field Data Entry exactly matches the pile name in Plot Plan (case-sensitive, no extra spaces).
Problem: Drive Time shows strange numbers or errors
Solution: Ensure start and end times are formatted as times, not text. Use format like "8:00 AM" or "14:30".
Problem: Status not updating correctly
Solution: Check that embedment and design embedment are numeric values (not text). Also verify tolerance setting in Dashboard C5.
Problem: Conditional formatting not showing colors
Solution: The formatting rules may have been cleared. Check Data → Conditional Formatting to restore them.
Problem: New rows don't have formulas
Solution: Copy formulas from the row above, or select the cell with the formula and drag the fill handle down.
© 2025 PileTrackerPro - Excel Template Version